## Pritthiraj
Pritthiraj
Sprint 1
Issue # | User Story Title/Task Title | Description | Story Points (1,2,3,5,8) | Duration | Deadline
12 | Create Service Layer | - Implemented methods to get users, create users, delete user, get all users. - implemented a signup method which takes a userDTO and stores a user in the database. - implemented a login feature that takes username (or studentID) and password and returns the corresponding user | 3 | 120 min | 2024-09-23
13 | Add Personal description to README | - Have to have background information on top of roles in README. | 0 | 15 min | 2024-09-23
14 | Retype minutes #1, 2, 3 according to new template | - fill in the relevant sections of the template with information from the existing meeting minutes | 0 | 30 min | 2024-09-21
19 | Write Comments for service layer | - Add Javadoc above each method to explain the method | 0 | 15 min | 2024-09-26
21 | Finish Sprint Plan for Sprint 1 | - Finalize the description for each issue, as well as the risk and priority levels | 0 | 25 min | 2024-09-29

## Daniel
Daniel
Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Duration | Date Completed
#3 | Init front end project | - Setup project with React, written in TypeScript and TailwindCSS - Outline the structure of compoenets & add variables for colour palletes | 1 | 30 | 2024-09-20
#20 | Retype minutes #1, 2 3 according to new template | - fill in the relevant sections of the template with information from the existing meeting minutes | 0 | 20 | 2024-09-21
#22 | Registration Component Figma | - a draft of the registration component respecting the color pallet - must be saved in the assets/figma directory pf front end as a .png | 1 | 40 | 2024-09-23
#23 | Registration Component | - respects FIGMA - behaves like a form - has both a proffessor and a student version - uses User Input and Button components | 3 | 120 | 2024-09-23
#40 | Reorganize front before submission | - remove duplicate images from /figma/ - add logo to all login/registration components - add all components to the App.tsx view - reorganize path to login components - reorganize path to figma images | 1 | 30 | 2024-09-23

## Viresh
Viresh
Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Duration (minutes) | Date Completed
4 | Initialize Spring Boot Project with Spring Initalizr | Initialize the project and push to github | 1 | 30 | 2024-09-20
10 | Create DTO | Create DTO to faciliate data transfer between frontend and backend | 1 | 15 | 2024-09-22
11 | Create Mapper | Convert objects from DTO to Entities | 1 | 30 | 2024-09-20
14 | Create user entity | Organize how objects will be mapped to MySQL database | 2 | 90 | 2024-09-22
16 | Create repository layer for login | Add custom queries to get users from database | 0 | 10 | 2024-09-23
32 | Populate Role database with existing roles | Ensure that Professor and Student roles exist in database | 0 | 20 | 2024-09-24

## Mohamed
Mohamed
Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Duration | Date Completed
4 | Input field | have a login or a password type (hide characters or not) styling as per the FIGMA | 1 | 50 | 23/09/2024
13 | Login Component | uses User Input and Button components to build a login comopnent respects FIGMA draft behaves like a form on submit (sends action when submit is pressed) | 1 | 15 | 24/09/2024
19 | Add personal description READ

## Nguyen
Nguyen
Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Duration | Date completed
5 | Figma login Page | Do a user interface for all the component for sprint 1 |  | 60 | 15/09/2024
8 | Button component | Make a button component in react and tailwind css | 1 | 60 | 23/09/2024
19 | Add personal description READ | Add a description in readme | 0 | 15 | 23/09/2024
13 | Login component | Combine all the component in pages using figma | 1 | 75 | 25/09/2024

## Mathieu
Mathieu
Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Duration(minutes | Deadline
13 | Add Personal description to README | -Added description of my role in the project | 0 | 15 min | 2024-09-20
12 | Create service layer | -added the service layer interface, did the setup for the user class and backend packages | 0 | 15 min | 2024-09-21
6 | Create controller layer to handle HTTP requests | - Create a controller layer that handles API requests | 1 | 30min | 2024-09-26
6 | Create controller layer to handle HTTP requests | - Connected the backend functions of Pritthiraj and Viresh to the frontend components of Daniel, Mohamed and Nguyen | 1 | 90min | 2024-09-27
6 | Create controller layer to handle HTTP requests | -Ajusted the format of the data that is sent from forntend to be readable from the backend | 2 | 120min | 2024-09-28
6 | Create controller layer to handle HTTP requests | -Collaborated with viresh and Pritthiraj to add cheks when signing In that would verify if the username was already used in the data base | 0 | 20 min | 2024-09-29