## Sheet1
Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Priority | Risk | Responsible | Deadline
1 | Init front end project | - Setup project with React, written in TypeScript and TailwindCSS - Outline the structure of compoenets & add variables for colour palletes | 1 | HIGH | HIGH | Daniel | 2024-09-20
2 | Initialize Spring Boot Project with Spring Initializer | - Setup backend with Spring Boot | 1 | HIGH | HIGH | Viresh | 2024-09-20
3 | Figma of Login Page | - Design and pick the appearance of the website | 0 | HIGH | LOW | Nguyen | 2024-09-26
4 | Input Field | - have a login or a password type (hide characters or not) - styling as per the FIGMA - error message (User not found, password) - password format (regex) | 1 | HIGH | MEDIUM | Mohamed | 2024-09-24
5 | Button Component | - create a button that emits event on click - respects the FIGMA draft | 1 | HIGH | MEDIUM | Nguyen | 2024-09-23
6 | Create controller layer to handle HTTP requests | - Create a controller layer that handles API requests - Implement a login and signup path that will use methods login and signup from the service layer | 3 | MEDIUM | HIGH | Mathieu | 2024-09-26
7 | Create DTO | - Create Data-Transfer object to model users | 1 | HIGH | MEDIUM | Viresh | 2024-09-22
8 | Create Mapper Package | - Create mapper package that will convert DTO to Entity and vice-versa | 1 | HIGH | LOW | Viresh | 2024-09-23
9 | Login Component | - uses User Input and Button components to build a login comopnent - respects FIGMA draft - behaves like a form on submit (sends action when submit is pressed) | 3 | MEDIUM | HIGH | Mohamed, Ngyuen | 2024-09-24
10 | Create User Entity | - Model the entry in a database and create the table | 1 | MEDIUM | HIGH | Viresh | 2024-09-22
11 | Create repository layer for login | - Write Method to fetch user by username or student by student ID - Return User Data for Authentication | 0 | LOW | MEDIUM | Viresh | 2024-09-23
12 | Create service layer | - Implements methods to get users, create users, delete user, get all users. - For this sprint, implement a signup method which takes a userDTO and stores a user in the database. - Also implement a login feature that takes username (or studentID) and password and returns the corresponding user | 3 | MEDIUM | HIGH | Pritthiraj | 2024-09-23
13 | Add Personal description to README | - Have to have background information on top of roles in README. | 0 | MEDIUM | LOW | Everyone | 2024-09-23
14 | Retype minutes #1, 2, 3 according to new template | - fill in the relevant sections of the template with information from the existing meeting minutes | 0 | LOW | LOW | Pritthiraj, Daniel, Viresh | 2024-09-21
15 | Registration Component Figma | - a draft of the registration component respecting the color pallet - must be saved in the assets/figma directory pf front end as a .png | 1 | HIGH | LOW | Daniel | 2024-09-23
16 | Registration Component | - respects FIGMA - behaves like a form - has both a proffessor and a student version - uses User Input and Button components | 3 | MEDIUM | HIGH | Daniel | 2024-09-23
17 | Populate Role database with existing roles | - Write a script that runs on start so that roles PROFESSOR and STUDENT already exist prior to adding users. | 0 | MEDIUM | MEDIUM | Viresh | 2024-09-24
18 | Reorganize front before submission | - remove duplicate images from /figma/ - add logo to all login/registration components - add all components to the App.tsx view - reorganize path to login components - reorganize path to figma images | 1 | LOW | HIGH | Daniel | 2024-09-26
19 | Write comments for service layer | - Add Javadoc above each method to explain the method | 0 | LOW | LOW | Pritthiraj | 2024-09-26
20 | Implement button and user-input components into login pages |  |  | MEDIUM | HIGH | Mohamed | 2024-09-29