## Pritthiraj
Pritthiraj
Sprint 1
Issue # | User Story Title/Task Title | Description | Story Points (1,2,3,5,8) | Duration | Deadline
12 | Create Service Layer | - Implemented methods to get users, create users, delete user, get all users. - implemented a signup method which takes a userDTO and stores a user in the database. - implemented a login feature that takes username (or studentID) and password and returns the corresponding user | 3 | 120 min | 2024-09-23
13 | Add Personal description to README | - Have to have background information on top of roles in README. | 0 | 15 min | 2024-09-23
14 | Retype minutes #1, 2, 3 according to new template | - fill in the relevant sections of the template with information from the existing meeting minutes | 0 | 30 min | 2024-09-21
19 | Write Comments for service layer | - Add Javadoc above each method to explain the method | 0 | 15 min | 2024-09-26
21 | Finish Sprint Plan for Sprint 1 | - Finalize the description for each issue, as well as the risk and priority levels | 0 | 25 min | 2024-09-29
Sprint 2
74 | Fetch Teammates List | - Implement a method to fetch teammates based on the group project. - Connect to the database to retrieve teammates associated with the logged-in user and the selected project. - Create a service that returns the list of teammates | 2 | 100 min | 2024-10-10
75 | Save Selected Teammates | - Implement a method to store selected teammates for evaluation. - Validate teammate selection and ensure only teammates from the same group can be selected. - Update the database with the selected teammates for evaluation. | 3 | 240 min | 2024-10-18
76 | Implement Rating Submission Logic | - Create a method to accept and store peer ratings and comments. - Define the rating scale (1-5) for the Cooperation dimension. - Store the cooperation rating, linking to the evaluator and evaluatee. | 1 | 60 min | 2024-10-20
77 | Validation of Rating Inputs | - Validate rating inputs (ensure ratings are within the 1-5 range). - Ensure all teammates selected for evaluation receive a rating. - Handle errors if ratings are incomplete or out of range. | 0 | 20 min | 2024-10-20
119 | Complete Sprint Planning for Sprint 2 | - Finalize the description for each issue, as well as the risk and priority levels | 0 | 25 min | 2024-10-24

## Daniel
Daniel
Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Duration (mins) | Date Completed
#3 | Init front end project | - Setup project with React, written in TypeScript and TailwindCSS - Outline the structure of compoenets & add variables for colour palletes | 1 | 30 | 2024-09-20
#20 | Retype minutes #1, 2 3 according to new template | - fill in the relevant sections of the template with information from the existing meeting minutes | 0 | 20 | 2024-09-21
#22 | Registration Component Figma | - a draft of the registration component respecting the color pallet - must be saved in the assets/figma directory pf front end as a .png | 1 | 40 | 2024-09-23
#23 | Registration Component | - respects FIGMA - behaves like a form - has both a proffessor and a student version - uses User Input and Button components | 3 | 120 | 2024-09-23
#40 | Reorganize front before submission | - remove duplicate images from /figma/ - add logo to all login/registration components - add all components to the App.tsx view - reorganize path to login components - reorganize path to figma images | 1 | 30 | 2024-09-23
Sprint 2
#65 | Delete Team FIGMA | - Design for Displaying Current Teams - Design for displaying number of team members | 1 | 15 | 2024-10-08
#66 | Delete Team Component | - Displays Current Teams - Display number of team members - Delete a single team - Unassign students from the team when its deleted | 1 | 30 | 2024-10-08
#91 | Redux to manage session information | set up Redux student slice with: student registration / login teacher registration / login user logou adjust reg/login views to use redux state public/protected routes only login/registration/welcome are available to non-signed in users can't access routes by editing url (it refreshes the page? and resets the redux session) backend readme with MySQL commands scripts to automate application start/stop (mysql, front, back servers (Linux only)) | 3 | 180 | 2024-10-23
#102 | Refactor Frontend | - file structure - break down components - export functions for reuse - wiki page with frontend development guidellines | 2 | 120 | 2024-10-16
#55 | Team Preview Component | - Should include: - team name - team members - respects FIGMA - take data as props - don't limit number of team members - limit the size of the team preview component | 1 | 30 | 2024-10-06
#56 | Team Overview FIGMA | - Should include: - team name - team members - respect color palette | 1 | 15 | 2024-10-03
#79 | Assessment View FIGMA | - Design a 5 point scale for student assessment (Cooperation dimension) - Design a comment field - Design a submit button | 1 | 20 | 2024-10-21
#80 | Implementing Assessment Component View | - Follow the Figma for design - Create a 5 point scale for student assessment (Cooperation dimension) - Add a comment field - Submit button - team slice to keep track of current team - allteams slice to keep track of all teams - assessslice to keep track of assessment info | 3 | 180 | 2024-10-26
13

## Viresh
Viresh
Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Duration (minutes) | Date Completed
4 | Initialize Spring Boot Project with Spring Initalizr | Initialize the project and push to github | 1 | 30 | 2024-09-20
10 | Create DTO | Create DTO to faciliate data transfer between frontend and backend | 1 | 15 | 2024-09-22
11 | Create Mapper | Convert objects from DTO to Entities | 1 | 30 | 2024-09-20
14 | Create user entity | Organize how objects will be mapped to MySQL database | 2 | 90 | 2024-09-22
16 | Create repository layer for login | Add custom queries to get users from database | 0 | 10 | 2024-09-23
32 | Populate Role database with existing roles | Ensure that Professor and Student roles exist in database | 0 | 20 | 2024-09-24
Sprint 2
73 | Store teams in database | Map teams to the MySQL database | 2 | 45 | 2024-10-07
72 | Team Creation Functionality | Implement API to create a team | 3 | 90 | 2024-10-07
94 | Integrate frontend team creation with backend | From team creation form, make api request to backend | 1 | 45 | 2024-10-13
97 | Setup CI pipeline for backend | Setup CI for Spring Boot Backend | 2 | 120 | 2024-10-14
98 | Display all current teams for user | API to get all the teams that a student is part of | 2 | 90 | 2024-10-17
100 | Return user info by id | API call to return a userDTO based on the provided ID | 2 | 60 | 2024-10-17
113 | Implement API to delete teams | API call to delete a team from the database | 1 | 30 | 2024-10-22
114 | Create API to get all students | API to get all students from the database | 1 | 30 | 2024-10-22
Sprint 3

## Mohamed
Mohamed
Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Duration (mins) | Date Completed
4 | Input field | have a login or a password type (hide characters or not) styling as per the FIGMA | 1 | 50 | 23/09/2024
13 | Login Component | uses User Input and Button components to build a login comopnent respects FIGMA draft behaves like a form on submit (sends action when submit is pressed) | 1 | 15 | 24/09/2024
19 | Add personal description READ |  | - | 15 | 24/09/2024
46 | TASK 2.2 React Router | - add router to project - add paths for login student/teacher - add paths for registration student/teacher - add success login page | 2 | 120 | 30/09/2024
Sprint 2
45 | TASK 2.1 File Import Query Button | button opens a 'open file' pop-up accept any .csv file save the file locally (under /src/resources/*.csv name of component is '/src/components/input/buttonOpenFile' notifies if success or not (using toastnotify) | 2 | 45 | 2024-07-10
61 | TASK 2.4 Team Dropdown Component | queries for the existing teams selects a single team from the drop down respects FIGMA | 2 | 50 | 2024-07-10
64 | TASK 2.7 Create Team | Figma all students that are not in a team displayed in a table select students (check-boxes) done button | 2 | 45 | 2024-10-10
68 | TASK 2.16 CI for frontend | must check that the app.tsx component loads | 2 | 90 | 22/10/2024
96 | TASK 4.1 Team Control (Student) Component | upon selection of a team display all teammates allows the selection of a teammate to grade | 3 | 60 | 22/10/2024

## Nguyen
Nguyen
Sprint 1
Issue # | User Story Title/Task Title | Story Points (1,2,3,5,8) | Duration (mins) | Date completed
5 | Figma login Page |  | 60 | 15/09/2024
8 | Button component | 1 | 60 | 23/09/2024
19 | Add personal description READ | 0 | 15 | 23/09/2024
13 | Login component | 1 | 75 | 25/09/2024
Sprint 2
|  | Description | Story points | Duration | Date completed
62 | Table Component | - Should alphabetically order the students - the columns should consist of: name, id, team component, average peer review grade - Respects FIGMA design | 3 | 180 minutes | 2024-10-10
60 | Dashboard student FIGMA | Student table Student sidebar to navigate Student choose team | 2 | 100 minutes | 20/10/2024

## Mathieu
Mathieu
Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Duration (mins) | Deadline
13 | Add Personal description to README | -Added description of my role in the project | 0 | 15 min | 2024-09-20
12 | Create service layer | -added the service layer interface, did the setup for the user class and backend packages | 0 | 15 min | 2024-09-21
6 | Create controller layer to handle HTTP requests | - Create a controller layer that handles API requests | 1 | 30min | 2024-09-26
6 | Create controller layer to handle HTTP requests | - Connected the backend functions of Pritthiraj and Viresh to the frontend components of Daniel, Mohamed and Nguyen | 1 | 90min | 2024-09-27
6 | Create controller layer to handle HTTP requests | -Ajusted the format of the data that is sent from forntend to be readable from the backend | 2 | 120min | 2024-09-28
6 | Create controller layer to handle HTTP requests | -Collaborated with viresh and Pritthiraj to add cheks when signing In that would verify if the username was already used in the data base | 0 | 20 min | 2024-09-29
Sprint 2
69 | Implement Functionality to Upload CSV File | - Create a file input field on the user interface to allow professors to select and upload a CSV file. - Implement backend logic to handle file parsing and validate the format of the CSV file. - Add error handling for invalid or corrupted CSV files. | 2 | 180 min | 2024-10-17 | 2024-10-23
70 | Parse the Uploaded CSV and Extract Student Info | - Create a parser to extract student IDs, names, and any other relevant data from the CSV. - Store student data in a temporary table or list for review before adding to the database. - Ensure CSV format and required fields (e.g., student ID, name) are validated. | 3 | 300 min | 2024-10-20 | 2024-10-23
78 | Implement Confirmation Logic | - Create a method to confirm and finalize the peer assessment submission. - Store the assessment status (submitted, pending) in the database. - Ensure that once submitted, the assessment cannot be edited. | 2 |  | 2024-10-24 | 2024-10-26