## Sprint 3
Sprint 3
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Priority | Risk | Responsible | Deadline
6.1 | Update Database Schema (Backend) | - Add columns for new dimensions (Conceptual Contribution, Practical Contribution, Work Ethic) and optional comment fields in the peer assessment table. | 1 | HIGH | MEDIUM | Pritthiraj | 2024-10-31
6.2 | Modify Service Layer for 4 Dimensions (Backend) | - Update the service layer to handle storing and retrieving ratings for all four dimensions, along with optional comments. | 2 | HIGH | MEDIUM | Pritthiraj | 2024-10-31
6.3 | Update Controller Logic for the Other Dimensions (Backend) | - Update the API endpoints to accept and process ratings and comments for all assessment dimensions. | 1 | HIGH | HIGH | Pritthiraj | 2024-10-31
6.4 | Update Peer Assessment Submission Logic (Backend) | - Modify existing submission logic to handle additional dimensions by adding the combined points and save optional comments in an array. | 1 | HIGH | MEDIUM | Pritthiraj | 2024-10-31
6.5 | Design UI for Additional Dimensions (Frontend) | - Update the peer assessment interface to include rating options for Conceptual Contribution, Practical Contribution, and Work Ethic, along with optional comment boxes for each. | 2 | HIGH | LOW | Daniel | 2024-10-31
6.6 | Implement Inputs Fields for Ratings (Frontend) | - Add interactive input fields (5-point scales) for each dimension, ensuring proper layout and styling. | 1 | HIGH | MEDIUM | Daniel | 2024-10-31
6.7 | Add Optional Comment Boxes (Frontend) | - Provide text areas under each rating scale for students to input optional comments. Ensure the UI clearly indicates that these fields are optional. | 1 | MEDIUM | LOW | Daniel | 2024-10-31
6.8 | Update Confirmation Page for Peer Assessment Submission (Frontend) | - Update the existing confirmation page that shows the student their ratings and comments before final submission, with the option to edit or confirm. | 1 | HIGH | MEDIUM | Daniel | 2024-10-31
6.9 | Api Calls to Send Ratings and Comment to Backend | - an API to send each of the ratings and the comment section into the array | 1 | LOW | MEDIUM | Daniel, Viresh | 2024-10-31
HIGH

## Sprint 2
Sprint 2
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Priority | Risk | Responsible | Deadline
2.1 | File Import Query Button | - Button opens a "open file" pop-up - Accepts a .csv file - Save the file locally (under /src/resources/*.csv - Name of component is '/src/components/input/buttonOpenFile' - Notifies if opening file is successful or not using toastnotify | 2 | HIGH | HIGH | Mohamed | 2024-10-07
2.2 | React Router | - Add router to project - It should add paths for login student/teacher - Adds paths for register student/teacher - Adds success login page | 3 | MEDIUM | HIGH | Mohamed | 2024-09-30
2.3 | Dashboard FIGMA | - table of students should be designed, for each should incude: - id - name - team - chose what team to assign student to (dropdown) - button to add students to table - respects color palette | 2 | HIGH | LOW | Nguyen | 2024-10-20
2.4 | Team Dropdown Component | - Queries for the existing teams - Selects a single team from the drop down - Respects FIGMA design | 1 | HIGH | LOW | Mohamed | 2024-10-07
2.5 | Table Component | - Should alphabetically order the students - the columns should consist of: name, id, team component, average peer review grade - Respects FIGMA design | 3 | HIGH | LOW | Nguyen | 2024-10-09
2.6 | Create / Remove Team Link with Existing Components | - create routes to page with a list of unassigned students - remove routes to a page with all teams - unassigned students of that team submit button |  | MEDIUM | HIGH | Mohamed | 2024-10-26
2.7 | Create Team | - Should show all students that are not in a team displayed in a table - Be able to select students using check-boxes - Should include a done button | 2 | HIGH | MEDIUM | Nguyen, Daniel, Mohamed | 2024-10-07
2.8 | Delete Team FIGMA | - Design for Displaying Current Teams - Design for displaying number of team members | 1 | HIGH | MEDIUM | Daniel | 2024-10-08
2.9 | Delete Team Component | - Displays Current Teams - Display number of team members - Delete a single team - Unassign students from the team when its deleted | 1 | HIGH | HIGH | Daniel | 2024-10-08
2024-02-10 | Implement Functionality to Upload CSV File | - Create a file input field on the user interface to allow professors to select and upload a CSV file. - Implement backend logic to handle file parsing and validate the format of the CSV file. - Add error handling for invalid or corrupted CSV files. | 2 | HIGH | HIGH | Mathieu | 2024-10-23
2.11 | Parse the Uploaded CSV and Extract Student Info | - Create a parser to extract student IDs, names, and any other relevant data from the CSV. - Store student data in a temporary table or list for review before adding to the database. - Ensure CSV format and required fields (e.g., student ID, name) are validated. | 3 | HIGH | HIGH | Mathieu | 2024-10-23
2.12 | Team Creation Functionality | - Create logic to group selected students into teams | 3 | HIGH | HIGH | Viresh | 2024-10-07
2.13 | Store Teams In Database | - Map student and teachers to their related teams | 2 | HIGH | HIGH
2.14 | CI for Frontend | - - Must check that the app.tsx component loads for Frontend CI | 2 |  | MEDIUM | Mohamed | 2024-10-23
2.15 | Redux to manage session information | - add a basic configuration of Redux (to be injected in the reset of functionality in future tasks) | 3 | HIGH | HIGH | Daniel | 2024-10-23
2.16 | Setup CI Pipeline in Backend | - Create CI pipeline for maven project | 2 | MEDIUM | MEDIUM | Viresh | 2024-10-23
2.17 | Refactor Frontend | - file structure - break down components - export functions for reuse | 2 | HIGH | LOW | Daniel | 2024-10-16
2.18 | Create a new CSV showcase page | - Shows the list of students after importing a CSV file | 2 | MEDIUM | LOW | Nguyen | 2024-10-26
2.19 | Create API to Get All Students | - An API to fetch all current students in the database - Used for professors to find students and add them to teams | 1 | HIGH | LOW | Viresh | 2024-10-22
2.2 | Sync Students Displayed with Backend via API calls + Team creation / deletion | make the 'all students' and add csv buttons available to Teachers only sync the students displayed wiht mySQL data add api calls to csv upload button team creation / deletion with database | 3 | HIGH | HIGH | Daniel | 2024-10-26
3.1 | Team Preview Component | - Should include: - team name - team members - respects FIGMA - take data as props - don't limit number of team members - limit the size of the team preview component | 1 | MEDIUM | MEDIUM | Daniel | 2024-10-06
3.2 | Team Overview FIGMA | - Should include: - team name - team members - respect color palette | 1 | MEDIUM | MEDIUM | Daniel | 2024-10-03
3.3 | Display all current teams for a user | Given a user ID, find all of the teams they are part of and return them as a list | 2 | MEDIUM | MEDIUM | Viresh | 2024-10-17
3.4 | Return User Info by ID | Given a user ID return all their information like name, username, teams that they are part of etc. | 2 | MEDIUM | MEDIUM | Viresh | 2024-10-20
3.5 | Implement API to Delete Teams | Given a teamID, remove the corresponding team from the database | 1 | MEDIUM | LOW | Viresh | 2024-10-26
4.1 | Team Control (Student) Component | - upon selection of a team - display all teammates - allows the selection of a teammate to grade | 2 |  | LOW | Mohamed | 2024-10-22
4.2 | Fetch Teammates List | - Implement a method to fetch teammates based on the group project. - Connect to the database to retrieve teammates associated with the logged-in user and the selected project. - Create a service that returns the list of teammates. | 2 | HIGH | MEDIUM | Pritthiraj | 2024-10-08
4.3 | Save Selected Teammates | - Implement a method to store selected teammates for evaluation. - Validate teammate selection and ensure only teammates from the same group can be selected. - Update the database with the selected teammates for evaluation. | 3 | HIGH | HIGH | Pritthiraj | 2024-10-18
4.4 | Integrate Frontend Team Creation with Backend | - Submit the API request to the backend - Return a confirmation message to the console | 1 | HIGH | LOW | Viresh | 2024-10-14
5.1 | Implement Rating Submission Logic | - Create a method to accept and store peer ratings and comments. - Define the rating scale (1-5) for the Cooperation dimension. - Store the cooperation rating, linking to the evaluator and evaluatee. | 1 | HIGH | HIGH | Pritthiraj | 2024-10-20
5.2 | Validation of Rating Inputs | - Validate rating inputs (ensure ratings are within the 1-5 range). - Ensure all teammates selected for evaluation receive a rating. - Handle errors if ratings are incomplete or out of range. | 0 | MEDIUM | MEDIUM | Pritthiraj | 2024-10-20
5.3 | Implement Confirmation Logic | - Create a method to confirm and finalize the peer assessment submission. - Store the assessment status (submitted, pending) in the database. - Ensure that once submitted, the assessment cannot be edited. | 2 | HIGH | MEDIUM | Mathieu | 2024-10-26
5.4 | Assessment View FIGMA | - Design a 5 point scale for student assessment (Cooperation dimension) - Design a comment field - Design a submit button | 1 | LOW | LOW | Daniel | 2024-10-21
5.5 | Implementing Assessment Component View | - Follow the Figma for design - Create a 5 point scale for student assessment (Cooperation dimension) - Add a comment field - Submit button - team slice to keep track of current team - allteams slice to keep track of all teams - assessslice to keep track of assessment info | 3 | LOW | HIGH | Daniel | 2024-10-26
5.6 | Add Confirmation Page | - Reference Number (like a transaction id) - Display new assessment (what it would look like) - Submit button - Cancel button - Print page button | 2 | LOW | LOW | Nguyen, Daniel | 2024-10-26
6.5 | Design UI for Additional Dimensions | Update the peer assessment interface to include rating options for Conceptual Contribution, Practical Contribution, and Work Ethic, along with optional comment boxes for each. | 0 | HIGH | HIGH | Daniel | 2024-10-26
6.6 | Implement Inputs Fields for Ratings | Add interactive input fields (5-point scales) for each dimension, ensuring proper layout and styling. | 0 | HIGH | HIGH | Daniel | 2024-10-26
6.7 | Add Optional Comment Boxes | Provide text areas under each rating scale for students to input optional comments. Ensure the UI clearly indicates that these fields are optional. | 0 | HIGH | HIGH | Daniel | 2024-10-26

## Sprint 1
Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Priority | Risk | Responsible | Deadline
1 | Init front end project | - Setup project with React, written in TypeScript and TailwindCSS - Outline the structure of compoenets & add variables for colour palletes | 1 | HIGH | HIGH | Daniel | 2024-09-20
2 | Initialize Spring Boot Project with Spring Initializer | - Setup backend with Spring Boot | 1 | HIGH | HIGH | Viresh | 2024-09-20
3 | Figma of Login Page | - Design and pick the appearance of the website | 0 | HIGH | LOW | Nguyen | 2024-09-26
4 | Input Field | - have a login or a password type (hide characters or not) - styling as per the FIGMA - error message (User not found, password) - password format (regex) | 1 | HIGH | MEDIUM | Mohamed | 2024-09-24
5 | Button Component | - create a button that emits event on click - respects the FIGMA draft | 1 | HIGH | MEDIUM | Nguyen | 2024-09-23
6 | Create controller layer to handle HTTP requests | - Create a controller layer that handles API requests - Implement a login and signup path that will use methods login and signup from the service layer | 3 | MEDIUM | HIGH | Mathieu | 2024-09-26
7 | Create DTO | - Create Data-Transfer object to model users | 1 | HIGH | MEDIUM | Viresh | 2024-09-22
8 | Create Mapper Package | - Create mapper package that will convert DTO to Entity and vice-versa | 1 | HIGH | LOW | Viresh | 2024-09-23
9 | Login Component | - uses User Input and Button components to build a login comopnent - respects FIGMA draft - behaves like a form on submit (sends action when submit is pressed) | 3 | MEDIUM | HIGH | Mohamed, Ngyuen | 2024-09-24
10 | Create User Entity | - Model the entry in a database and create the table | 1 | MEDIUM | HIGH | Viresh | 2024-09-22
11 | Create repository layer for login | - Write Method to fetch user by username or student by student ID - Return User Data for Authentication | 0 | LOW | MEDIUM | Viresh | 2024-09-23
12 | Create service layer | - Implements methods to get users, create users, delete user, get all users. - For this sprint, implement a signup method which takes a userDTO and stores a user in the database. - Also implement a login feature that takes username (or studentID) and password and returns the corresponding user | 3 | MEDIUM | HIGH | Pritthiraj | 2024-09-23
13 | Add Personal description to README | - Have to have background information on top of roles in README. | 0 | MEDIUM | LOW | Everyone | 2024-09-23
14 | Retype minutes #1, 2, 3 according to new template | - fill in the relevant sections of the template with information from the existing meeting minutes | 0 | LOW | LOW | Pritthiraj, Daniel, Viresh | 2024-09-21
15 | Registration Component Figma | - a draft of the registration component respecting the color pallet - must be saved in the assets/figma directory pf front end as a .png | 1 | HIGH | LOW | Daniel | 2024-09-23
16 | Registration Component | - respects FIGMA - behaves like a form - has both a proffessor and a student version - uses User Input and Button components | 3 | MEDIUM | HIGH | Daniel | 2024-09-23
17 | Populate Role database with existing roles | - Write a script that runs on start so that roles PROFESSOR and STUDENT already exist prior to adding users. | 0 | MEDIUM | MEDIUM | Viresh | 2024-09-24
18 | Reorganize front before submission | - remove duplicate images from /figma/ - add logo to all login/registration components - add all components to the App.tsx view - reorganize path to login components - reorganize path to figma images | 1 | LOW | HIGH | Daniel | 2024-09-26
19 | Write comments for service layer | - Add Javadoc above each method to explain the method | 0 | LOW | LOW | Pritthiraj | 2024-09-26
20 | Implement button and user-input components into login pages |  |  | MEDIUM | HIGH | Mohamed | 2024-09-29