## Pritthiraj
Pritthiraj
Sprint 1
Issue # | User Story Title/Task Title | Description | Story Points (1,2,3,5,8) | Duration | Deadline
12 | Create Service Layer | - Implemented methods to get users, create users, delete user, get all users. - implemented a signup method which takes a userDTO and stores a user in the database. - implemented a login feature that takes username (or studentID) and password and returns the corresponding user | 3 | 120 min | 2024-09-23
13 | Add Personal description to README | - Have to have background information on top of roles in README. | 0 | 15 min | 2024-09-23
14 | Retype minutes #1, 2, 3 according to new template | - fill in the relevant sections of the template with information from the existing meeting minutes | 0 | 30 min | 2024-09-21
19 | Write Comments for service layer | - Add Javadoc above each method to explain the method | 0 | 15 min | 2024-09-26
21 | Finish Sprint Plan for Sprint 1 | - Finalize the description for each issue, as well as the risk and priority levels | 0 | 25 min | 2024-09-29
Sprint 2
74 | Fetch Teammates List | - Implement a method to fetch teammates based on the group project. - Connect to the database to retrieve teammates associated with the logged-in user and the selected project. - Create a service that returns the list of teammates | 2 | 100 min | 2024-10-10
75 | Save Selected Teammates | - Implement a method to store selected teammates for evaluation. - Validate teammate selection and ensure only teammates from the same group can be selected. - Update the database with the selected teammates for evaluation. | 3 | 240 min | 2024-10-18
76 | Implement Rating Submission Logic | - Create a method to accept and store peer ratings and comments. - Define the rating scale (1-5) for the Cooperation dimension. - Store the cooperation rating, linking to the evaluator and evaluatee. | 1 | 60 min | 2024-10-20
77 | Validation of Rating Inputs | - Validate rating inputs (ensure ratings are within the 1-5 range). - Ensure all teammates selected for evaluation receive a rating. - Handle errors if ratings are incomplete or out of range. | 0 | 20 min | 2024-10-20
119 | Complete Sprint Planning for Sprint 2 | - Finalize the description for each issue, as well as the risk and priority levels | 0 | 25 min | 2024-10-24
Sprint 3
130 | Update Database Schema (Backend) | - Add columns for new dimensions (Conceptual Contribution, Practical Contribution, Work Ethic) and optional comment fields in the peer assessment table. | 1 | 20 min | 2024-10-31
131 | Modify Service Layer for 4 Dimensions (Backend) | - Update the service layer to handle storing and retrieving ratings for all four dimensions, along with optional comments. | 2 | 90 min | 2024-10-31
132 | Update Controller Logic for the Other Dimensions (Backend) | - Update the API endpoints to accept and process ratings and comments for all assessment dimensions. | 1 | 20 min | 2024-10-31
133 | Update Peer Assessment Submission Logic (Backend) | - Modify existing submission logic to handle additional dimensions by adding the combined points and save optional comments in an array. | 1 | 30 mn | 2024-10-31
162 | Implement Function for Detailed View Data | - Create function for displaying individual ratings and comments | 2 | 120 min | 2024-11-10
165 | Display Available Unevaluated Teammates for Evaluator (Backend) | - Create a feature that displays all the available teammates that a student (evaluator) has not yet evaluated. - The list should be unique for each team the evaluator is part of. - Once a teammate has been evaluated, they should not appear in the list for future evaluations by the same evaluator in that specific team. | 1 | 40 min | 2024-11-02
173 | Unit tests for TeamService and AuthController | Write unit tests for the classes Test all methods | 2 | 150 min | 2024-11-07
192 | Professor Grade Approval/Deny Feature | Implement logic allowing professors to approve or deny gambled grades. If approved, update the student’s official grade with the gambled value. If denied, discard the gambled grade and retain the original score. This endpoint should: Update the database with approval or denial status. Return a success response or error in case of issues. | 2 | 150 min | 2024-11-10
Sprint 4
211 | Create Reset Password Endpoint | - Implement an API to accept student ID and new password. - Validate the student ID and hash the new password before saving it. - Update the database with the new password. | 1 | 30 min | 2024-11-18
212 | Implement Password Security | - Ensure secure password hashing - Add validation for password strength. | 2 | 100 min | 2024-11-17
N/A | Added comments to necessary methods | - All methods that didn't have any comments were given comments | 0 | 45 min | 2024-11-26
N/A | Unit Test for Reset Password | - Write unit tests for the reset password method | 1 | 30 min | 2024-11-26

## Daniel
Daniel
Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Duration (mins) | Date Completed
#3 | Init front end project | - Setup project with React, written in TypeScript and TailwindCSS - Outline the structure of compoenets & add variables for colour palletes | 1 | 30 | 2024-09-20
#20 | Retype minutes #1, 2 3 according to new template | - fill in the relevant sections of the template with information from the existing meeting minutes | 0 | 20 | 2024-09-21
#22 | Registration Component Figma | - a draft of the registration component respecting the color pallet - must be saved in the assets/figma directory pf front end as a .png | 1 | 40 | 2024-09-23
#23 | Registration Component | - respects FIGMA - behaves like a form - has both a proffessor and a student version - uses User Input and Button components | 3 | 120 | 2024-09-23
#40 | Reorganize front before submission | - remove duplicate images from /figma/ - add logo to all login/registration components - add all components to the App.tsx view - reorganize path to login components - reorganize path to figma images | 1 | 30 | 2024-09-23
Sprint 2
#65 | Delete Team FIGMA | - Design for Displaying Current Teams - Design for displaying number of team members | 1 | 15 | 2024-10-08
#66 | Delete Team Component | - Displays Current Teams - Display number of team members - Delete a single team - Unassign students from the team when its deleted | 1 | 30 | 2024-10-08
#91 | Redux to manage session information | set up Redux student slice with: student registration / login teacher registration / login user logou adjust reg/login views to use redux state public/protected routes only login/registration/welcome are available to non-signed in users can't access routes by editing url (it refreshes the page? and resets the redux session) backend readme with MySQL commands scripts to automate application start/stop (mysql, front, back servers (Linux only)) | 3 | 180 | 2024-10-23
#102 | Refactor Frontend | - file structure - break down components - export functions for reuse - wiki page with frontend development guidellines | 2 | 120 | 2024-10-16
#55 | Team Preview Component | - Should include: - team name - team members - respects FIGMA - take data as props - don't limit number of team members - limit the size of the team preview component | 1 | 30 | 2024-10-06
#56 | Team Overview FIGMA | - Should include: - team name - team members - respect color palette | 1 | 15 | 2024-10-03
#79 | Assessment View FIGMA | - Design a 5 point scale for student assessment (Cooperation dimension) - Design a comment field - Design a submit button | 1 | 20 | 2024-10-21
#80 | Implementing Assessment Component View | - Follow the Figma for design - Create a 5 point scale for student assessment (Cooperation dimension) - Add a comment field - Submit button - team slice to keep track of current team - allteams slice to keep track of all teams - assessslice to keep track of assessment info | 3 | 180 | 2024-10-26
#123 | Sync Students Displayed with Backend via API calls + Team creation / deletion | make the 'all students' and add csv buttons available to Teachers only sync the students displayed wiht mySQL data add api calls to csv upload button team creation / deletion with database | 3 | 220 | 2024-10-26
#81 | Add Confirmation Page | - Reference Number (like a transaction id) - Display new assessment (what it would look like) - Submit button - Cancel button - Print page button | 2 | 50 | 2024-10-26
Sprint 3
#134 | Design UI for Additional Dimensions | Update the peer assessment interface to include rating options for Conceptual Contribution, Practical Contribution, and Work Ethic, along with optional comment boxes for each. | 0 | 10 | 2024-10-31
#135 | Implement Inputs Fields for Ratings | Add interactive input fields (5-point scales) for each dimension, ensuring proper layout and styling. | 0 | 10 | 2024-10-31
#136 | Add Optional Comment Boxes | Provide text areas under each rating scale for students to input optional comments. Ensure the UI clearly indicates that these fields are optional. | 0 | 10 | 2024-10-31
#137 | Update Confirmation Page for Peer Assessment Submission (Frontend) | - Update the existing confirmation page that shows the student their ratings and comments before final submission, with the option to edit or confirm. | 1 | 30 | 2024-10-31
#138 | Api Calls to Send Ratings and Comment to Backend | - an API to send each of the ratings and the comment section into the array | 1 | 30 | 2024-10-31
#167 | Display Available Unevaluated Teammates for Evaluator (Frontend) | - do not allow evaluation of evaluated teammates using the backend api | 2 | 60 | 2024-11-03
#160 | Create Detailed View | - Instructor selects the Detailed View option. - Instructor views a detailed breakdown for each student, showing ratings across all assessment dimensions. - Instructor sees comments provided by evaluators for each student. - Instructor can filter data by assessment dimension (e.g., Cooperation, Work Ethic) for in-depth analysis. | 2 | 90 | 2024-11-02
#184 | Link Summary and Detailed Views from Backend | - create a new store slice - use api calls to get summary view data - use api calls to get detailed view data - integrate data from the new slice with the existing components (detailed & summary views) | 3 | 180 | 2024-11-10
Sprint 4
#185 | Link Gambling to Backend | Add api calls to the gamble frontend actions create new slice to manage gamble data | 2 | 120 | 2024-11-16
#177 | Update detailed view to show if the student has gambled | In the detailed view create a field that shows if the student has gambled or not If they have, show their current grade and the grade they obtained through gambling Have an approve button, that updates the current grade with the gambled grade | 1 | 40 | 2024-11-16
#221 | Fix SonarQube Code Analysis for FronEnd | reduce Security, Reliability, Maintainability, Hotsports Reviewed, coverage and Duplications to minimum ideally get As everywhere | 2 | 70 | 2024-11-25

## Viresh
Viresh
Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Duration (minutes) | Date Completed
4 | Initialize Spring Boot Project with Spring Initalizr | Initialize the project and push to github | 1 | 30 | 2024-09-20
10 | Create DTO | Create DTO to faciliate data transfer between frontend and backend | 1 | 15 | 2024-09-22
11 | Create Mapper | Convert objects from DTO to Entities | 1 | 30 | 2024-09-20
14 | Create user entity | Organize how objects will be mapped to MySQL database | 2 | 90 | 2024-09-22
16 | Create repository layer for login | Add custom queries to get users from database | 0 | 10 | 2024-09-23
32 | Populate Role database with existing roles | Ensure that Professor and Student roles exist in database | 0 | 20 | 2024-09-24
Sprint 2
73 | Store teams in database | Map teams to the MySQL database | 2 | 45 | 2024-10-07
72 | Team Creation Functionality | Implement API to create a team | 3 | 90 | 2024-10-07
94 | Integrate frontend team creation with backend | From team creation form, make api request to backend | 1 | 45 | 2024-10-13
97 | Setup CI pipeline for backend | Setup CI for Spring Boot Backend | 2 | 120 | 2024-10-14
98 | Display all current teams for user | API to get all the teams that a student is part of | 2 | 90 | 2024-10-17
100 | Return user info by id | API call to return a userDTO based on the provided ID | 2 | 60 | 2024-10-17
113 | Implement API to delete teams | API call to delete a team from the database | 1 | 30 | 2024-10-22
114 | Create API to get all students | API to get all students from the database | 1 | 30 | 2024-10-22
Sprint 3
156 | Setup JUnit for Backend Unit Tests | Configure JUnit and Mockito for uniit tests and integrate with CI | 5 | 180 | 2024-11-04
174 | Unit tests for UserService, UserController, TeamController | Write unit tests for the classes and all methods | 2 | 60 | 2024-11-04
178 | Backend for Gambling Feature | Return the result of a gambling call. When professor approves, update current grade with gambled grade | 2 | 40 | 2024-11-08
190 | Dice Roll Logic |  | 1 | 20 | 2024-11-08
191 | Gambled grade submission | Stores gambled grade as a separate entity | 2 | 90 | 2024-11-08
Sprint 4
204 | API call to get gambled grade | Get information related to gambling feature | 2 | 60 | 2024-11-18
222 | Refactor code for SonarQube Analusis | Fix maintainability and reliability issues | 2 | 120 | 2024-11-22
N/A | Create Backend Guidelines | Write guidelines listing the proper practices to writing backend code | 0 | 20 | 2024-11-25

## Mohamed
Mohamed
Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Duration (mins) | Date Completed
4 | Input field | have a login or a password type (hide characters or not) styling as per the FIGMA | 1 | 50 | 23/09/2024
13 | Login Component | uses User Input and Button components to build a login comopnent respects FIGMA draft behaves like a form on submit (sends action when submit is pressed) | 1 | 15 | 24/09/2024
19 | Add personal description READ |  | - | 15 | 24/09/2024
46 | TASK 2.2 React Router | - add router to project - add paths for login student/teacher - add paths for registration student/teacher - add success login page | 2 | 120 | 30/09/2024
Sprint 2
45 | TASK 2.1 File Import Query Button | button opens a 'open file' pop-up accept any .csv file save the file locally (under /src/resources/*.csv name of component is '/src/components/input/buttonOpenFile' notifies if success or not (using toastnotify) | 2 | 45 | 2024-07-10
61 | TASK 2.4 Team Dropdown Component | queries for the existing teams selects a single team from the drop down respects FIGMA | 1 | 50 | 2024-07-10
64 | TASK 2.7 Create Team | Figma all students that are not in a team displayed in a table select students (check-boxes) done button | 2 | 45 | 2024-10-10
68 | TASK 2.14 CI for frontend | must check that the app.tsx component loads | 5 | 120 | 22/10/2024
96 | TASK 4.1 Team Control (Student) Component | upon selection of a team display all teammates allows the selection of a teammate to grade | 2 | 90 | 22/10/2024
Sprint 3
155 | TEST 1.1: Setup Cypress For Frontend Unit Tests | "- Add necessary dependencies and ensure that tests are running in CI - Install and configure Cypress in the frontend environment. - Implement in CI so that it runs automatically" | 5 | 200 | 2024-07-11
| Dice interface | Create a dice interface create a button to function to activate the feature 2 dices alert box when button click that reminds the rules | 2 | 120 | 2024-09-11
Sprint 4
| TASK 9.3 Create Reset Password UI | - Design a page with a form for student ID and new password fields. - Add a "Forgot Password" hyperlink on the login page. - Validate input. | 2 | 60 | 21/11/2024
| TASK 9.5 Update Dashboard UI | - Add a section on the student dashboard for notifications. - Display notification message: "You have received a new evaluation" or no notification if none exist. | 2 | 45 | 21/11/2024
| TASK 9.6 Integrate Notification API | - Fetch notifications using the backend API. - Ensure real-time updates if notifications change | 2 | 120 | 21/11/2024

## Nguyen
Nguyen
Sprint 1
Issue # | User Story Title/Task Title | Story Points (1,2,3,5,8) | Duration (mins) | Date completed
5 | Figma login Page |  | 60 | 15/09/2024
8 | Button component | 1 | 60 | 23/09/2024
19 | Add personal description READ | 0 | 15 | 23/09/2024
13 | Login component | 1 | 75 | 25/09/2024
Sprint 2
|  | Description | Story points | Duration | Date completed
62 | Table Component | - Should alphabetically order the students - the columns should consist of: name, id, team component, average peer review grade - Respects FIGMA design | 3 | 180 minutes | 2024-10-10
60 | Dashboard student FIGMA | Student table Student sidebar to navigate Student choose team | 2 | 100 minutes | 20/10/2024
148 | Confirmation page | Assessment detail | 5 | 45 minutes | 22/10/2024
107 | CSV SHOWCASE | button component csv | 2 | 30 minutes | 2024-09-10
Sprint 3
#159 | Summary View | Student table with all the grades | 7 | 30 minutes | 2024-03-11
#176 | Gambling feature | Profile, Gambling page and interface | 8 | 100 minutes | 2024-06-11
#188 | Fixed routing | Side bar for students and smooth nav | just fixing bugs | 30 minutes | 2024-08-11
#128 | AT 6 Dimension Based Assessment | Record | 6 | 5 minutes | 2024-10-11
#163 | AT 7 Teacher Dashboard | Record | 7 | 5 minutes | 2024-10-11
#202 | AT 8 Special feature gambling | Record | 8 | 5 minutes | 2024-10-11
Sprint 4
227 | Notification | CODE review | 8 | 10 minutes | 22/11/2024
226 | Sonarqube quality update | CODE review | 9 | 30 minutes | 22/11/2024
127 | AT5 | Test review | 7 | 5MINUTES | 22/11/2024

## Mathieu
Mathieu
Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story Points (1,2,3,5,8) | Duration (mins) | Deadline
13 | Add Personal description to README | -Added description of my role in the project | 0 | 15 min | 2024-09-20
12 | Create service layer | -added the service layer interface, did the setup for the user class and backend packages | 0 | 15 min | 2024-09-21
6 | Create controller layer to handle HTTP requests | - Create a controller layer that handles API requests | 1 | 30min | 2024-09-26
6 | Create controller layer to handle HTTP requests | - Connected the backend functions of Pritthiraj and Viresh to the frontend components of Daniel, Mohamed and Nguyen | 1 | 90min | 2024-09-27
6 | Create controller layer to handle HTTP requests | -Ajusted the format of the data that is sent from forntend to be readable from the backend | 2 | 120min | 2024-09-28
6 | Create controller layer to handle HTTP requests | -Collaborated with viresh and Pritthiraj to add cheks when signing In that would verify if the username was already used in the data base | 0 | 20 min | 2024-09-29
Sprint 2
69 | Implement Functionality to Upload CSV File | - Create a file input field on the user interface to allow professors to select and upload a CSV file. - Implement backend logic to handle file parsing and validate the format of the CSV file. - Add error handling for invalid or corrupted CSV files. | 2 | 180 min | 2024-10-17
70 | Parse the Uploaded CSV and Extract Student Info | - Create a parser to extract student IDs, names, and any other relevant data from the CSV. - Store student data in a temporary table or list for review before adding to the database. - Ensure CSV format and required fields (e.g., student ID, name) are validated. | 3 | 300 min | 2024-10-20
78 | Implement Confirmation Logic | - Create a method to confirm and finalize the peer assessment submission. - Store the assessment status (submitted, pending) in the database. - Ensure that once submitted, the assessment cannot be edited. | 2 | 240 min | 2024-10-26
Sprint 3
161 | Implement Summary View data Route | Create an overall grading system for the students Make sure it is implemented in the database | 3 | 180 min | 2024-11-08
172 | Unit tests for FileController and StorageService | Write unit tests for those two classes | 2 | 120 min | 2024-11-10
Test each method
Couple of examples can be found in UserServiceTests and TeamControllerTests
Sprint 4
217 | Create Notification API | -Implement an API to check if a student has been evaluated. -Fetch evaluation status from the database and return the appropriate notification. | 1 | 60 min | 2024-11-18
218 | Handle Notification Logic | -Implement logic to trigger notifications when a student is assessed. -Ensure notifications are accurate and only displayed when necessary. -Add a field in database to track if a student has been evaluated. | 2 | 120 min | 2024-11-17